## Amol
Sr No | Date | Work | Start Date | End Date | Estimated Complition Date of Project | Status
1 | 2014-02-17 | Working on Biomatric attendance (R&D), CMS Project | 2014-02-17 |  |  | In Progress
2 | 2014-02-18 | Working on Biomatric attendance (R&D), CMS Project, M.K Service Demo of BTS given | 2014-02-17 |  |  | In Progress
3 | 2014-02-19 | Accounting System SMS Integration | 2014-02-19 | 2014-02-19 |  | Complete
4 | 2014-02-20 | Accounting System: Worked on Main office client transfer amount to Branch office | 2014-02-20 | 2014-02-20 |  | Complete
5 | 2014-02-21 | Working on Biomatric attendance (R&D), CMS Project, Emil Auto Responder (R&D) | 2014-02-21 |  |  | In Progress
6 | 2014-02-24 | Working on Biomatric attendance (R&D), CMS Project | 2014-02-21 |  |  | In Progress
| 2014-02-25 | Working on Biomatric attendance CMS Project | 2014-02-21 |  |  | In Progress
|  | Accounting System : Branch Name, Branch Address and Contact No. included In SMS | 2014-02-25 | 2014-02-25 |  | Complete

## Milind
Sr No | Work
1 | HMS Demo Error Hanling
2 | OPDBill
3 | CMS Over look

## Tushar
Sr No | Date | Work | Start Date | End Date | Estimated Complition Date of Project | Status
1 | 2014-02-17 | CMS HR Module (Testing) | 2014-02-17 | 2014-02-19 |  | In Progress
2 | 2014-02-18 | CMS HR Module (Testing) | 2014-02-17 | 2014-02-19 |  | Complete
3 | 2014-02-19 | HMS Project Validation | 2014-02-17 | 2014-02-19 |  | Complete
4 | 2014-02-20 | CMS(Testing)-Admin Module | 2014-02-20 | 2014-02-22 |  | In Progress
|  | Emil Auto Responder (R&D) | 2014-02-20 | 2014-02-20 |  | Complete
5 | 2014-02-21 | CMS(Testing)-Admin Module | 2014-02-20 | 2014-02-21 |  | Complete
| 2014-02-24 | HMS(Validation) Certificate Module | 2014-02-24 | 2014-02-25 |  | In Progress
| 2014-02-25 | HMS(Validation) Certificate Module | 2014-02-24 | 2014-02-25 |  | Complete

## Kiran
Sr No | Date | Work | Start Date | End Date | Estimated Complition Date of Project | Status | Team Member Name
1 | 2014-02-17 | Admin Module-Batch Allotment | 2014-02-17 | 2014-02-18 |  | In Progress | Kiran
| 2014-02-17 | Admin Module-Fees Payment against total fees and admission completed | 2014-02-17 | 2014-02-18 |  | In Progress | Deepak
| 2014-02-17 | Admin Module-Coding of Compose SMS to student, parent, employee | 2014-02-17 | 2014-02-17 |  | Complete | Yogesh
| 2014-02-17 | Absent |  |  |  |  | Seema, Tarannum
| 2014-02-17 | Admin-Faculty I-card Generation | 2014-02-17 | 2014-02-18 |  | In Progress | Hemant
| 2014-02-17 | Absent |  |  |  |  | Meera
2 | 2014-02-18 | Add Acadmic Year to All Admin Pages | 2014-02-18 | 2014-02-18 |  | Complete | Kiran
|  | Admin Module-Fees Payment against total fees and admission completed | 2014-02-17 | 2014-02-18 |  | In Progress | Deepak
|  | Study Material and Assingment | 2014-02-18 | 2014-02-19 |  | In Progress | Yogesh
Seema, Tarannum
|  | Admin-Faculty I-card Generation | 2014-02-17 | 2014-02-18 |  | In Progress | Hemant
|  | Search Document | 2014-02-18 | 2014-02-20 |  | In Progress | Meera
| 2014-02-19 | Class Attendance | 2014-02-18 | 2014-02-19 |  | In Progress | Kiran
|  | Absent |  |  |  |  | Deepak
|  | Study Material and Assingment | 2014-02-18 | 2014-02-19 |  | Complete | Yogesh
Seema, Tarannum
|  | Admin-Faculty I-card Generation | 2014-02-17 | 2014-02-18 |  | In Progress | Hemant
|  | Search Document | 2014-02-18 | 2014-02-20 |  | In Progress | Meera
| 2014-02-20 | [5 empty] | Kiran
|  | Fees Payment Receipt(Formatting & Design Remaining) | 2014-02-20 | 2014-02-20 |  | Complete | Deepak
|  | Fees Installments | 2014-02-20 | 2014-02-21 |  | In Progress | Deepak
|  | Faculty department assinging | 2014-02-20 | 2014-02-21 |  | In Progress | Yogesh
Seema, Tarannum
Hemant
Meera
| 2014-02-21 | Save Subject Wise student Attendance | 2014-02-20 | 2014-02-21 |  | Complete | Kiran
|  | SuperAdmin,Admin: Testing Error And Solve IT | 2014-02-20 | 2014-02-22 |  | In Progress | Kiran
|  | Fees Payment Receipt Completed | 2014-02-21 | 2014-02-21 |  | Complete | Deepak
|  | Fees Installments Data shown on form Save Remaining | 2014-02-21 |  |  | In Progress | Deepak
|  | Resolving Issues on Upload Attendance Page | 2014-02-21 | 2014-02-21 |  | In Progress | Deepak
|  | Faculty department assinging | 2014-02-20 | 2014-02-21 |  | Complete | Yogesh
|  | HR Test Cases | 2014-02-21 |  |  | In Progress | Yogesh
Seema, Tarannum
Hemant
Meera
| 2014-02-24 | Admin Testing And Error Solving | 2014-02-24 | 2014-02-25 |  | In Progress | Kiran
|  | Admin Master Testing & Issue Resolve | 2014-02-24 | 2014-02-24 |  | Complete | Deepak
|  | On Leave |  |  |  |  | Yogesh
|  | Admin Experience Letter | 2014-02-24 | 2014-02-25 |  | In Progress | Hemant
|  | Admin Set Leave | 2014-02-24 | 2014-02-25 |  | In Progress | Tarannum
|  | Admin Set Leave For All | 2014-02-24 | 2014-02-26 |  | In Progress | Seema
|  | Print Document | 2014-02-24 | 2014-02-25 |  | In Progress | Meera
| 2014-02-25 | Admin Testing And Error Solving | 2014-02-24 | 2014-02-25 |  | Complete | Kiran
|  | AddStaff Resolve Errors | 2014-02-25 | 2014-02-25 |  | Complete | Deepak
|  | Testing Error Solving ,Add Functionality in AddFees | 2014-02-25 |  |  | In Progress | Yogesh
|  | Admin Experience Letter | 2014-02-24 | 2014-02-25 |  | In Progress | Hemant
|  | Admin Set Leave | 2014-02-24 | 2014-02-25 |  | In Progress | Tarannum
|  | Admin Set Leave For All | 2014-02-24 | 2014-02-26 |  | In Progress | Seema
|  | Print Document | 2014-02-24 | 2014-02-25 |  | In Progress | Meera
Note on C5: SHREE: SMS Coding is completed testing is remaining